## Sheet1
Requirement ID | Requirement Description | Scenario ID | Test Case ID | Test Case Description | Execution Status | Defect ID
REQ-LOG-01 | Verify that with valid username and password, login should work | SCN-001 | TC-001 | Verify that with valid username and password, login should work | Pass | NA
REQ-LOG-02 | Verify that login should fail with invalid password | SCN-002 | TC-002 | Verify that login should fail with invalid password | Fail | BUG-LOGIN-002
REQ-LOG-03 | Verify that login should validate required fields when username or password is empty | SCN-003 | TC-003 | Verify that login should validate required fields when username or password is empty | Fail | BUG-LOGIN-003
REQ-APPT-01 | Appointment booking and confirmation | SCN-004 | TC-004 | Verify that user should be able to book an appointment with valid inputs | Pass | NA
REQ-APPT-02 | The system shall prevent appointment booking when the selected visit date is earlier than the current date. | SCN-005 | TC-005 | Verify that booking should be prevented when Visit Date is a past date | Pass | NA
REQ-APPT-03 | The system shall validate all mandatory fields in the appointment booking form and prevent submission until all required information is provided. | SCN-006 | TC-006 | Verify that booking should validate required fields before submission | Pass | NA
REQ-APPT-04 | After successful appointment booking with all user-entered details accurately reflected in History | SCN-007 | TC-007 | Verify that confirmation page should display correct booking details after successful booking | Pass | NA
REQ-APPT-05 | Appointment history management | SCN-008 | TC-008 | Verify that booked appointment should appear in History page | Pass | NA
REQ-LOG-04 | Logout and protected page access control | SCN-009 | TC-009 | Verify that logout should end session and redirect to homepage/login | Pass | NA
REQ-USAB-01 | Responsive UI across devices | SCN-010 | TC-010 | Verify that pages should render correctly on common viewport sizes (mobile/tablet/desktop) | Pass | NA
REQ-NET-01 | Cross-browser compatibility | SCN-011 | TC-011 | Verify that UI should be consistent across supported browsers | Pass | NA
REQ-NAV-01 | Keyboard accessibility support | SCN-012 | TC-012 | Validate that form fields should have labels and support keyboard navigation | Pass | NA
REQ-SEC-01 | Duplicate appointment prevention | SCN-013 | TC-013 | Verify that double-clicking 'Book Appointment' should not create duplicate bookings | Pass | NA
REQ-ACC-02 | Network error handling during booking | SCN-014 | TC-014 | Verify that temporary network loss should be handled gracefully during booking | Pass | NA
REQ-USAB-02 | Menu visibility and accessibility | SCN-015 | TC-015 | Validate that the hamburger/menu items should be accessible and labeled | Pass | NA
REQ-NET-03 | Session timeout enforcement | SCN-016 | TC-016 | Verify that session should timeout or logout correctly based on expected behavior | Pass | NA
REQ-USAB-02 | Image accessibility compliance | SCN-017 | TC-017 | Validate that decorative and informative images should have appropriate alt attributes | Pass | NA
REQ-NET-04 | Verify that form data should persist or warn user on refresh to prevent data loss | SCN-018 | TC-018 | Verify that form data should persist or warn user on refresh to prevent data loss | Fail | BUG-DATA-018